Annex 3

PROJECT MATURITY DEVELOPMENT PLAN

This form is a Programme template. It may not be altered or amended in any way

For evaluation purposes of concept notes, by project maturity is meant an indication of the ability of the project partnership to bring the project idea to a state of implementation. An applicant with a high degree of project maturity would be considered to have better chances of timely project success than applicants with a lower degree of project maturity.

The purpose of the project maturity development plan (PMDP) is to describe what is needed for a project idea to grow from a concept to a ready-for-implementation project. PMDP is a way to measure the growth of a concept note in terms of documentation, preparatory steps and outcome - ideally, it should be an achieved project readiness (e.g. obtained permits and approvals from responsible institutions; developed and approved works/technical design, incl. detailed bill of quantities in case of works; detailed procurement plan, etc.) when submitting the full project proposal. You will have not less than 6 months for your concept note to evolve in a full project proposal.

The feasibility and the consistency of the PMDP with the project idea and its legal compliance is subject to assessment. Therefore, at this stage, it is very important for you to identify all key preparatory steps (incl. related paperwork and documents) that would ensure smooth and predictable start of the project upon contracting. If these steps are not carefully envisaged, that may jeopardize the success of the project and therefore, it may weaken the justification for grant awarding.

Please, fill in the table below by clearly describing and detailing to a maximum possible extent the following information:

- The preparatory steps of the PMDP in terms of actions/documents that are legally required for you to perform the project’s activities;

- project objective – link each identified preparatory step for achieving project maturity at the full project proposal with the corresponding project objective

- each partner’s role in the implementation of the PMDP;

- the timeline for the implementation of the PMDP;

Some hints how to develop your PMDP:

- Make sure you follow the provisions of the respective national legislation, regulating the planning and the performance of the works and the supply activities under your project. In case of Bulgaria, these are (list is not exhausted) the Regional Development Act, Spatial Development Act, Environmental Protection Law, Public Procurement Law, etc. In case of North Macedonia these are (list is not exhausted) Law on Balanced Regional Development, Law on the Environment, Law on Public Procurement, еtc.

- Do not miss to consider environment and climate risks related to your project idea, particularly in relation to works and supply;

- Please, be clear and concise when filling out the table. Each identified action/step should be described in a separate row. Also, the provided information in column ‘Implementation time’ should refer to expected output.

Title of the concept note:

Lead partner:

Project partners (in native and English language):

Project duration: (number of months)

|  | Preparatory step for achieving project maturity at the full project proposal | Reference to legal/administrative act | Expected output | Competence body | Partners competence and responsibility | Project objective | Implementation time (start…end) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | E.g. actions needed to perform investment planning | What legal/administrative act/s (incl. articles) determine the need to perform that action/step? | What is the final result/output of the action/step? (e.g. decision of the municipal council; feasibility study, environmental impact (EI) screening decisions and/or other EI assessments, etc.) | Who is/are the body/bodies responsible for delivering the expected output/s | Which partner is competent to run this action/step and assume the responsibility for its management | Indicate the project objective whose achievement depends on the identified preparatory step/action and or document | Calendar months |
|  | E.g. obtaining various licenses, permits, approvals | What legal/administrative act/s (incl. articles) determine the need to perform that action/step? | E.g. Approved works/technical design, incl. detailed bill of quantities (for works), building permits, etc. | Who is/are the body/bodies responsible for delivering the expected output/s | Which partner is competent to run this action/step and assume the responsibility for its management Here you may also specify whether the planned investment will take place in part or in the entire property | Indicate the project objective whose achievement depends on the identified preparatory step/action and or document | Calendar months |
|  | E.g. development of indicative procurement plan (which includes works, supply and services activities) | What legal/administrative act/s (incl. articles) determine the need to perform that action/step? | E.g. Detailed technical specification of first tender procedures | Who is/are the body/bodies responsible for delivering the expected output/s (if different from project partners) | Here you can specify each partner’s role in the preparation and implementation of each tender procedure according to partner’s competences and roles in the achievement of project objectives | Indicate the project objective whose achievement depends on the identified preparatory step/action and or document | Calendar months |